## Technical Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
Technical Issues
The table below lists the issues discovered on the network and scanned computer endpoints that have been assessed during the Technical Review and automated scans. The summary below ranks individual issues based upon their potential risk to the information system while providing guidance on which issues to address by priority. To mitigate global risk and improve the health of the system, address issues with higher risk values first.
Risk Priority | Risk Response | Impact | Likelihood | Implementation Status | Weaknesses | Affects | Responsible Office/Organization | Resource Estimates (Funded/Unfunded/Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility
Low | Transfer | Low | High | Complete | Unsupported Operating Systems: Computers found using an operating system that is no longer supported. Unsupported operating systems no longer receive vital security patches and present an inherent risk. | DESKPC-35EGQCC / fe80::a03d:7987:35a4:7be%3,176.16.1.179 / Windows 10 Enterprise Version 2004 DESKPC-09UPSPO / 176.16.1.169 / Windows 10 Pro Version 1909 DESKPC-I595F9F / 176.16.1.102 / Windows 10 Enterprise Version 2004 DESKPC-N883DVI / 176.16.1.124 / Windows 10 Enterprise Version 2004 DESKPC-FOP1ENA / 176.16.1.136 / Windows 10 Enterprise Version 2004 DESKPC-5GTVFB3 / 176.16.1.131 / Windows 10 Enterprise Version 2004 DESKPC-3IC4R57 / fe80::9e8:6dd8:fe24:8c05%6,176.16.1.142 / Windows 10 Enterprise Version 2004 DESKPC-B9ETSS8 / 176.16.1.145 / Windows 10 Enterprise Version 2004 DESKPC-1QSHT11 / 176.16.1.140 / Windows 10 Enterprise Version 2004 DESKPC-Q9TQ4IM / 176.16.1.69 / Windows 10 Pro Version 2004 DESKPC-KLR129U / 176.16.1.51 / Windows 10 Pro Version 2004 DESKPC-ELBLDBS / 176.16.1.133 / Windows 10 Enterprise Version 2004 DESKPC-FEQIJCC / 176.16.1.146 / Windows 10 Enterprise Version 2004 DESKPC-4PF2ICP / 176.16.1.177 / Windows 10 Pro Version 1909 DESKPC-HQJ7BG2 / 176.16.1.139 / Windows 10 Enterprise Version 2004 | New York, NY USA | Unfunded | Dec-31-2025 | Upgrade or replace computers with operating systems that are no longer supported. |  | Security and compliance assessment | Complete | IT Operations
Very High | Mitigate | Very Low | High | Complete | Excessive security patches missing on computers: Security patches are missing on computers. Maintaining proper security patch levels helps prevent unauthorized access and the spread of malicious software. Excessive is defined as missing four or more patches. | APPSVR01 / fe80::4183:7729:9818:eb0f%6,176.16.1.14 / Windows Server 2016 Standard DESKPC-35EGQCC / fe80::a03d:7987:35a4:7be%3,176.16.1.179 / Windows 10 Enterprise Version 2004 | New York, NY USA | Funded | Dec-31-2025 | Address patching on computers missing 4+ security patches. |  | Security and compliance assessment | Complete | IT Operations
Very Low | Mitigate | High | High | Planned | Anti-spyware not up to date: Up to date anti-spyware definitions are required to properly prevent the spread of malicious software. Some anti-spyware definitions were found to not be up to date. | Computer: DESKPC-F6CKERQ IP Address: 176.16.1.171 Security Center: Windows Defender Computer: DESKPC-BDJFFLG IP Address: 176.16.1.170 Security Center: Windows Defender Computer: DESKPC-LIFRCFU IP Address: 176.16.1.172 Security Center: Windows Defender Computer: DESKPC-35EGQCC IP Address: 176.16.1.179 Security Center: Windows Defender Computer: WRKSTN10-4 IP Address: 176.16.1.149 Security Center: Windows Defender |  | Funded | Dec-31-2025 | Ensure anti-spyware definitions are up to date on specified computers. |  | Security and compliance assessment | Ongoing | IT Operations
Low | Mitigate | High | Low | Not Applicable | Potential disk space issue: 3 computers were found with significantly low free disk space. | DESKPC-4PF2ICP - C: : 0.05 GB free | New York, NY USA | Unfunded | Dec-31-2025 | Free or add additional disk space for the specified drives. |  | Security and compliance assessment | Complete | IT Operations
Low | Mitigate | Low | Moderate | Not Implemented | Significantly high number of Domain Administrators: More than 30% of the users are in the Domain Administrator group and have unfettered access to files and system resources. Compromised Domain Administrator accounts pose a higher threat than typical users and may lead to a breach. | abwfrcmbr / A Branaugh ajwfrcmbr / A Jensen aswfrcmbr / A Smith dwfrcmbr / Dora Baxter dkwfrcmbr / D Kindle dwwfrcmbr / D White jswfrcmbr / J Shearing jwwfrcmbr / J Westerfield lwwfrcmbr / L Wilson mgwfrcmbr / M Green mpwfrcmbr / M Peters mwwfrcmbr / M Warly pkwfrcmbr / P Kettering pswfrcmbr / P Sulu skwfrcmbr / S Kulynee spwfrcmbr / S Podsekin thwfrcmbr / T Harris uwfrcmbr / unitbdr admin wpwfrcmbr / W Paulson ydwfrcmbr / Yami Dareloth ylwfrcmbr / Y Leland | New York, NY USA | Unfunded | Dec-31-2025 | Evaluate the need to have more than 30% of users in the Domain Administrator group and limit administrative access to the minimum necessary. |  | Security and compliance assessment | Ongoing | Access Security Operations
Low | Mitigate | Low | Low | Complete | User password set to never expire: User accounts with passwords set to never expire present a risk of use by unauthorized users. They are more easily compromised than passwords that are routinely changed. | MYCO.COM\aswfrcmbr / A Smith MYCO.COM\dwfrcmbr / Dora Baxter MYCO.COM\dkwfrcmbr / D Kindle MYCO.COM\jswfrcmbr / J Shearing MYCO.COM\jwwfrcmbr / J Westerfield MYCO.COM\lwwfrcmbr / L Wilson MYCO.COM\mgwfrcmbr / M Green MYCO.COM\mpwfrcmbr / M Peters MYCO.COM\pkwfrcmbr / P Kettering MYCO.COM\spwfrcmbr / S Podsekin MYCO.COM\thwfrcmbr / T Harris MYCO.COM\ydwfrcmbr / Yami Dareloth MYCO.COM\ylwfrcmbr / Y Leland MYCO.COM\ajwfrcmbr / A Jensen MYCO.COM\dwwfrcmbr / D White MYCO.COM\mtalman / M Talman MYCO.COM\mwwfrcmbr / M Warly MYCO.COM\pswfrcmbr / P Sulu MYCO.COM\uwfrcmbr / unitbdr admin MYCO.COM\wpwfrcmbr / W Paulson | New York, NY USA | Funded | Dec-31-2025 | Investigate all accounts with passwords set to never expire and configure them to expire regularly. |  | Security and compliance assessment | Complete | Access Security Operations
Low | Mitigate | Low | Low | Not Implemented | Operating system in Extended Support: Computers are using an operating system that is in Extended Support. Extended Support is a warning period before an operating system is no longer supported by the manufacturer and will no longer receive support or patches. | DESKPC-RB3LBP3 / 176.16.1.108 / Windows 10 Enterprise 2015 LTSB APPSVR01 / fe80::4183:7729:9818:eb0f%6,176.16.1.14 / Windows Server 2016 Standard SQL01 / 176.16.1.17 / Windows Server 2012 R2 Standard EXCH01 / 176.16.1.15 / Windows Server 2012 R2 Standard FS01 / 176.16.1.16 / Windows Server 2016 Standard SQL02 / 176.16.1.21 / Windows Server 2016 Standard DCTRL01 / 176.16.1.12 / Windows Server 2016 Standard DCTRL02 / 176.16.1.13 / Windows Server 2016 Standard | New York, NY USA | Funded | Dec-31-2025 | Upgrade computers that have operating systems in Extended Support before end of life. |  | Security and compliance assessment | Ongoing | IT Operations
Low | Mitigate | Low | Low | Not Applicable | Inactive computers: Computers have not checked in during the past 30 days. | WRKSTN7-2 / 176.16.1.115 / Windows 7 Professional WRKSTN8-3 / 176.16.1.136 / Windows 8.1 Pro WRKSTN8-2 / 176.16.1.131 / Windows 8.1 Pro BDR01 / 176.16.1.140 / Windows Server 2016 Standard WRKSTN10-2 / 176.16.1.143 / Windows 10 Enterprise WRKSTN8-1 / 176.16.1.128 / Windows 8.1 Pro WRKSTN7-1 / 176.16.1.126 / Windows 7 Professional WRKSTN10-3 / 176.16.1.141 / Windows 10 Enterprise WRKSTN8-4 / 176.16.1.137 / Windows 8.1 Pro WS2012IT / 176.16.1.135 / Windows Server 2012 Standard Evaluation RFHVNDA1 / 176.16.1.11 / Windows Server 2016 Standard | New York, NY USA | Unfunded | Dec-31-2025 | Investigate the list of inactive computers and determine if they should be removed from Active Directory, rejoined to the network, logged into by authorized users, or powered on. |  | Security and compliance assessment | Complete | HR Department
Very High | Transfer | Low | Low | Not Implemented | User has not logged on to domain in 30 days: Users have not logged on to domain in 30 days. A user that has not logged in for an extended period of time could be a former employee or vendor. | ajwfrcmbr / A Jensen arom / Axel Rom Administrator / Administrator dwwfrcmbr / D White ebaldwin / Edward Baldwin fowardslash / fowared slash jknightling / Jorge Knightling jasus / Jeremy Asus jgilligan / Julia Gilligan jkalo / Jessica Kalo jchestnut / Janet Chestnut jconway / Joseph Conway jdelaney / Jonah Delaney mwwfrcmbr / M Warly mjohnson / Maxwell Johnson mtalman / M Talman pwalker / Paula Walker pswfrcmbr / P Sulu sjane / Sonny Jane tshelman / Terri Shelman uwfrcmbr / unitbdr admin wpwfrcmbr / W Paulson | New York, NY USA | Funded | Dec-31-2025 | Disable or remove user accounts for users that have not logged on to active directory in 30 days. |  | Security and compliance assessment | Ongoing | HR Department
High | Mitigate | High | High | Not Implemented | Password complexity not enabled: Enforcing password complexity limits the ability of an attacker to acquire a password through brute force. | APPSVR01 DESKPC-35EGQCC DESKPC-534MS45 | New York, NY USA | Funded | Dec-31-2025 | Enable password complexity to assure that network user account passwords are secure. |  | Security and compliance assessment | Ongoing | IT Operations
High | Transfer | Moderate | Moderate | Not Implemented | Automatic screen lock not turned on.: Automatic screen lock prevents unauthorized access when users leave their computers. Having no screen lock enabled allows unauthorized access to network resources. | APPSVR01 DESKPC-35EGQCC DESKPC-3IC4R57 DESKPC-534MS45 | New York, NY USA | Funded | Dec-31-2025 | Enable automatic screen lock on the specified computers. |  | Security and compliance assessment | Ongoing | IT Operations

## Control Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
Control Issues
The table below lists the issues discovered as a result of a Controls Assessment that was performed before this Plan of Action and Milestones was generated. The summary below ranks individual issues based upon their potential risk to the assessed business entity while providing guidance on which issues to address by risk priority, impact, and likelihood.
Risk Priority | Risk Response | Impact | Likelihood | Control ID | Control Text | Implementation Status | Weaknesses | Responsible Office/Organization | Resource Estimates (Funded / Unfunded / Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility | Related Requirement ID
Very Low | Transfer | Very Low | Very Low | CIS3.5 | Securely Dispose of Data: Securely dispose of data as outlined in the enterprise’s documented data management process. Ensure the disposal process and method are commensurate with the data sensitivity. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: Securely Dispose of Data |  | Security and compliance assessment | Ongoing | Data Protection Office | ID.AM-08
High | Mitigate | High | High | CIS7.2 | Establish and Maintain a Remediation Process: Establish and maintain a risk-based remediation strategy documented in a remediation process, with monthly, or more frequent, reviews. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: Establish and Maintain a Remediation Process |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-08
High | Mitigate | High | High | CIS11.2 | Perform Automated Backups : Perform automated backups of in-scope enterprise assets. Run backups weekly, or more frequently, based on the sensitivity of the data. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: Perform Automatted Backups |  | Security and compliance assessment | Ongoing | IT Operations | PR.DS-11
High | Mitigate | High | High | CIS15.3 | Classify Service Providers: Classify service providers. Classification consideration may include one or more characteristics, such as data sensitivity, data volume, availability requirements, applicable regulations, inherent risk, and mitigated risk. Update and review classifications annually, or when significant enterprise changes occur that could impact this Safeguard. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Imtplement the control: Classify Service Providers |  | Security and compliance assessment | Ongoing | Security Operations | GV.SC-04
High | Mitigate | High | High | CIS16.1 | Establish and Maintain a Secure Application Development Process: Establish and maintain a secure application development process. In the process, address such items as: secure application design standards, secure coding practices, developer training, vulnerability management, security of third-party code, and application security testing procedures. Review and update documentation annually, or when significant enterprise changes occur that could impact this Safeguard. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 |  |  | Security and compliance assessment | Ongoing | Security Operations | PR.PS-06
High | Mitigate | High | High | CIS17.9 | Establish and Maintain Security Incident Thresholds: Establish and maintain security incident thresholds, including, at a minimum, differentiating between an incident and an event. Examples can include: abnormal activity, security vulnerability, security weakness, data breach, privacy incident, etc. Review annually, or when significant enterprise changes occur that could impact this Safeguard. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 |  |  | Security and compliance assessment | Ongoing | Security Operations | RS.MA-05
High | Mitigate | High | High | CRI.EX.DD-03.01 | Technology & Cybersecurity Risk Assessment.01: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.01: The organization reviews, evaluates, and risk assesses a prospective critical third party's cybersecurity program, including its ability to identify, assess, monitor, and mitigate its cyber risks; the completeness of its policies and procedures; the strength of its technical and administrative controls; and the coverage of its internal and independent control testing programs. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.01: The organization reviews, evaluates, and risk assesses a prospective critical third party's cybersecurity program, including its ability to identify, assess, monitor, and mitigate its cyber risks; the completeness of its policies and procedures; the strength of its technical and administrative controls; and the coverage of its internal and independent control testing programs. |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-10
High | Mitigate | High | High | CRI.EX.DD-03.02 | Technology & Cybersecurity Risk Assessment.02: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.02: The organization reviews, evaluates, and risk assesses a prospective critical third party's business continuity program, to include business impact analyses, risk assessments, continuity plans, disaster recovery plans, technology resilience architecture, and response and recovery plans, test plans, and test results. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.02: The organization reviews, evaluates, and risk assesses a prospective critical third party's business continuity program, to include business impact analyses, risk assessments, continuity plans, disaster recovery plans, technology resilience architecture, and response and recovery plans, test plans, and test results. |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-10
High | Mitigate | High | High | CRI.EX.DD-03.03 | Technology & Cybersecurity Risk Assessment.03: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.03: The organization reviews, evaluates, and risk assesses a prospective critical third party's incident response program, to include monitoring and alerting capabilities, incident reporting procedures and protocols, and capabilities for event analysis, problem resolution, and forensic investigation. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-03.03: The organization reviews, evaluates, and risk assesses a prospective critical third party's incident response program, to include monitoring and alerting capabilities, incident reporting procedures and protocols, and capabilities for event analysis, problem resolution, and forensic investigation. |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-10
High | Mitigate | High | High | CRI.EX.DD-04.01 | Product & Service Due Diligence.01: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-04.01: The organization defines and implements procedures for assessing the compatibility, security, integrity, and authenticity of externally-developed or externally-sourced applications, software, software components, and firmware before deployment and upon any major change. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-04.01: The organization defines and implements procedures for assessing the compatibility, security, integrity, and authenticity of externally-developed or externally-sourced applications, software, software components, and firmware before deployment and upon any major change. |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-09
High | Mitigate | High | High | CRI.EX.DD-04.02 | Product & Service Due Diligence.02: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-04.02: The organization reviews and evaluates any technologies or information systems proposed to support a third party's services or activities, to include compatibility with the organization's technology and cybersecurity architectures, interactions and interfaces with existing systems, security controls, operational management and support requirements, and suitability to the task. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - EX.DD-04.02: The organization reviews and evaluates any technologies or information systems proposed to support a third party's services or activities, to include compatibility with the organization's technology and cybersecurity architectures, interactions and interfaces with existing systems, security controls, operational management and support requirements, and suitability to the task. |  | Security and compliance assessment | Ongoing | Security Operations | ID.RA-09
High | Mitigate | High | High | CRI.GV.PO-02.01 | Policy & Procedure Review & Update: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.PO-02.01: The cybersecurity policy is regularly reviewed, revised, and communicated under the leadership of a designated Cybersecurity Officer (e.g., CISO) to address changes in the risk profile and risk appetite, the evolving threat environment, and new technologies, products, services, and interdependencies. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.PO-02.01: The cybersecurity policy is regularly reviewed, revised, and communicated under the leadership of a designated Cybersecurity Officer (e.g., CISO) to address changes in the risk profile and risk appetite, the evolving threat environment, and new technologies, products, services, and interdependencies. |  | Security and compliance assessment | Ongoing | Executive Management | GV.PO-02
High | Mitigate | High | High | CRI.GV.RM-05.01 | Lines of Communication.01: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-05.01: The organization has a process for monitoring its technology, cybersecurity, and third-party risks, including escalating those risks that exceed risk appetite to management and identifying risks with the potential to impact multiple operating units. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-05.01: The organization has a process for monitoring its technology, cybersecurity, and third-party risks, including escalating those risks that exceed risk appetite to management and identifying risks with the potential to impact multiple operating units. |  | Security and compliance assessment | Ongoing | Executive Management | GV.RM-05
High | Mitigate | High | High | CRI.GV.RM-05.02 | Lines of Communication.02: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-05.02: The organization establishes minimum requirements for its third-parties that include how the organizations will communicate and coordinate in times of emergency, including: 1) Joint maintenance of contingency plans; 2) Responsibilities for responding to incidents, including forensic investigations; 3) Planning and testing strategies that address severe events in order to identify single points of failure that would cause wide-scale disruption; and 4) Incorporating the potential impact of an incident into their BCM process and ensure resilience capabilities are in place. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-05.02: The organization establishes minimum requirements for its third-parties that include how the organizations will communicate and coordinate in times of emergency, including: 1) Joint maintenance of contingency plans; 2) Responsibilities for responding to incidents, including forensic investigations; 3) Planning and testing strategies that address severe events in order to identify single points of failure that would cause wide-scale disruption; and 4) Incorporating the potential impact of an incident into their BCM process and ensure resilience capabilities are in place. |  | Security and compliance assessment | Ongoing | Executive Management | GV.RM-05
High | Mitigate | High | High | CRI.GV.RM-07.01 | Strategic Opportunities: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-07.01: The organization has mechanisms in place to ensure that strategies, initiatives, opportunities, and emerging technologies (e.g., artificial intelligence, quantum computing, etc.) are evaluated both in terms of risks and uncertainties that are potentially detrimental to the organization, as well as potentially advantageous to the organization (i.e., positive risks). | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.RM-07.01: The organization has mechanisms in place to ensure that strategies, initiatives, opportunities, and emerging technologies (e.g., artificial intelligence, quantum computing, etc.) are evaluated both in terms of risks and uncertainties that are potentially detrimental to the organization, as well as potentially advantageous to the organization (i.e., positive risks). |  | Security and compliance assessment | Ongoing | Executive Management | GV.RM-07
High | Mitigate | High | High | CRI.GV.SC-03.01 | Supply Chain Risk Management Integration: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.SC-03.01: The organization's third-party risk management strategy and program aligns with and supports its enterprise, technology, cybersecurity, and resilience risk management frameworks and programs. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - GV.SC-03.01: The organization's third-party risk management strategy and program aligns with and supports its enterprise, technology, cybersecurity, and resilience risk management frameworks and programs. |  | Security and compliance assessment | Ongoing | Executive Management | GV.SC-03
High | Mitigate | High | High | CRI.ID.IM-01.01 | Continuous Improvements Evaluation.01: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.01: Technology, cybersecurity, and resilience controls are regularly assessed and/or tested for design and operating effectiveness. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.01: Technology, cybersecurity, and resilience controls are regularly assessed and/or tested for design and operating effectiveness. |  | Security and compliance assessment | Ongoing | Executive Management | ID.IM-01
High | Mitigate | High | High | CRI.ID.IM-01.02 | Continuous Improvements Evaluation.02: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.02: The organization implements a regular process to collect, store, report, benchmark, and assess trends in actionable performance indicators and risk metrics (e.g., threat KRIs, security incident metrics, vulnerability metrics, and operational measures). | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.02: The organization implements a regular process to collect, store, report, benchmark, and assess trends in actionable performance indicators and risk metrics (e.g., threat KRIs, security incident metrics, vulnerability metrics, and operational measures). |  | Security and compliance assessment | Ongoing | Executive Management | ID.IM-01
High | Mitigate | High | High | CRI.ID.IM-01.03 | Continuous Improvements Evaluation.03: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.03: The organization establishes specific objectives, performance criteria, benchmarks, and tolerance limits to identify areas that have improved or are in need of improvement over time. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.03: The organization establishes specific objectives, performance criteria, benchmarks, and tolerance limits to identify areas that have improved or are in need of improvement over time. |  | Security and compliance assessment | Ongoing | Executive Management | ID.IM-01
High | Mitigate | High | High | CRI.ID.IM-01.04 | Continuous Improvements Evaluation.04: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.04: Technology and cybersecurity programs include elements designed to assess, manage, and continually improve the quality of program delivery in addressing stakeholder requirements and risk reduction. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.04: Technology and cybersecurity programs include elements designed to assess, manage, and continually improve the quality of program delivery in addressing stakeholder requirements and risk reduction. |  | Security and compliance assessment | Ongoing | Executive Management | ID.IM-01
High | Mitigate | High | High | CRI.ID.IM-01.05 | Continuous Improvements Evaluation.05: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.05: The organization's third-party risk management program is regularly assessed, reported on, and improved. | Not Implemented | Control partially implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - ID.IM-01.05: The organization's third-party risk management program is regularly assessed, reported on, and improved. |  | Security and compliance assessment | Ongoing | Executive Management | ID.IM-01
High | Mitigate | High | High | CRI.PR.AA-02.01 | Identity Binding to Credentials: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.AA-02.01: The organization authenticates identity, validates the authorization level of a user before granting access to its systems, limits the use of an account to a single individual, and attributes activities to the user in logs and transactions. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.AA-02.01: The organization authenticates identity, validates the authorization level of a user before granting access to its systems, limits the use of an account to a single individual, and attributes activities to the user in logs and transactions. |  | Security and compliance assessment | Ongoing | Executive Management | PR.AA-02
High | Mitigate | High | High | CRI.PR.AA-04.01 | Identity Assertions: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.AA-04.01: Access credential and authorization mechanisms for internal systems and across security perimeters (e.g., leveraging directory services, directory synchronization, single sign-on, federated access, credential mapping, etc.) are designed to maintain security, integrity, and authenticity. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.AA-04.01: Access credential and authorization mechanisms for internal systems and across security perimeters (e.g., leveraging directory services, directory synchronization, single sign-on, federated access, credential mapping, etc.) are designed to maintain security, integrity, and authenticity. |  | Security and compliance assessment | Ongoing | Security Operations | PR.AA-04
High | Mitigate | High | High | CRI.PR.IR-03.01 | Resilience Measures: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.IR-03.01: The organization implements mechanisms (e.g., failsafe, load balancing, hot swaps, redundant equipment, alternate services, backup facilities, etc.) to achieve resilience requirements in normal and adverse situations. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - PR.IR-03.01: The organization implements mechanisms (e.g., failsafe, load balancing, hot swaps, redundant equipment, alternate services, backup facilities, etc.) to achieve resilience requirements in normal and adverse situations. |  | Security and compliance assessment | Ongoing | Security Operations | PR.IR-03
High | Mitigate | High | High | CRI.RC.RP-05.01 | Asset Integrity Restoration.01: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-05.01: The organization maintains documented procedures for sanitizing, testing, authorizing, and returning systems to service following an incident or investigation. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-05.01: The organization maintains documented procedures for sanitizing, testing, authorizing, and returning systems to service following an incident or investigation. |  | Security and compliance assessment | Ongoing | Security Operations | RC.RP-05
High | Mitigate | High | High | CRI.RC.RP-05.02 | Asset Integrity Restoration.02: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-05.02: Business, technology, cybersecurity, and relevant third-party stakeholders confirm that systems, data, and services have been returned to functional and secure states and that a stable operational status has been achieved. | Not Implemented | Control not implemented | New York, NY USA | Unfunded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-05.02: Business, technology, cybersecurity, and relevant third-party stakeholders confirm that systems, data, and services have been returned to functional and secure states and that a stable operational status has been achieved. |  | Security and compliance assessment | Ongoing | Security Operations | RC.RP-05
High | Mitigate | High | High | CRI.RC.RP-06.01 | End-of-Incident Determination: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-06.01: Incident management activities are closed under defined conditions and documentation to support subsequent post-mortem review, process improvement, and any follow-on activities is collected and verified. | Planned | Control not implemented | New York, NY USA | Funded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RC.RP-06.01: Incident management activities are closed under defined conditions and documentation to support subsequent post-mortem review, process improvement, and any follow-on activities is collected and verified. |  | Security and compliance assessment | Ongoing | Executive Management | RC.RP-06
High | Mitigate | High | High | CRI.RS.AN-07.01 | Incident Data Collection & Preservation: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RS.AN-07.01: Incident-related forensic data is captured, secured, and preserved in a manner supporting integrity, provenance, and evidentiary value. | Planned | Control not implemented | New York, NY USA | Funded | 2025-12-24 | Implement the control: NIST CSF 2.0 Informative Reference - CRI Profile v2.0 - RS.AN-07.01: Incident-related forensic data is captured, secured, and preserved in a manner supporting integrity, provenance, and evidentiary value. |  | Security and compliance assessment | Ongoing | Security Operations | RS.AN-07

## Requirements Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
Requirements Issues
The table below lists the issues discovered as a result of a Requirements Assessment that was performed before this Plan of Action and Milestones was generated. The summary below ranks individual issues based upon their potential risk to the assessed business entity's compliance with the selected IT Security and/or Regulatory standards while providing guidance on which issues to address by risk priority, impact, and likelihood.
Risk Priority | Risk Response | Impact | Likelihood | Standard | Variant/Level | Requirement ID | Requirement Text | Implementation Status | Weaknesses | Responsible Office/Organization | Resource Estimates (Funded / Unfunded / Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility | Related Control ID
High | Mitigate | High | High | NIST CSF | 2.0 | GV.PO-02 | Policy & Procedure Review & Update: GV.PO-02: Policy for managing cybersecurity risks is reviewed, updated, communicated, and enforced to reflect changes in requirements, threats, technology, and organizational mission. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Policy & Procedure Review & Update |  | Security and compliance assessment | Ongoing | Executive Management | CRI.GV.PO-02.01
High | Mitigate | High | High | NIST CSF | 2.0 | GV.RM-05 | Lines of Communication: GV.RM-05: Lines of communication across the organization are established for cybersecurity risks, including risks from suppliers and other third parties. | Complete | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-02-10 | Address the requirement: Lines of Communication |  | Security and compliance assessment | Ongoing | Executive Management | CRI.GV.RM-05.01, CRI.GV.RM-05.02
High | Mitigate | High | High | NIST CSF | 2.0 | GV.RM-07 | Strategic Opportunities: GV.RM-07: Strategic opportunities (i.e., positive risks) are characterized and are included in organizational cybersecurity risk discussions. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Unfunded | 2025-03-12 | Address the requirement: Strategic Opportunities |  | Security and compliance assessment | Ongoing | Executive Management | CRI.GV.RM-07.01
High | Mitigate | High | High | NIST CSF | 2.0 | GV.SC-03 | Supply Chain Risk Management Integration: GV.SC-03: Cybersecurity supply chain risk management is integrated into cybersecurity and enterprise risk management, risk assessment, and improvement processes. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Unfunded | 2025-03-12 | Address the requirement: Supply Chain Risk Management Integration |  | Security and compliance assessment | Ongoing | Executive Management | CRI.GV.SC-03.01
High | Mitigate | High | High | NIST CSF | 2.0 | GV.SC-04 | Supplier Identification & Prioritization: GV.SC-04: Suppliers are known and prioritized by criticality. | Complete | Standard Requirement not Addressed | New York, NY USA | Unfunded | 2025-02-10 | Address the requirement: Supplier Identification & Prioritization |  | Security and compliance assessment | Ongoing | Security Operations | CIS15.1, CIS15.3
High | Mitigate | High | High | NIST CSF | 2.0 | ID.AM-08 | Asset Life Cycle Management: ID.AM-08: Systems, hardware, software, services, and data are managed throughout their life cycles. | Complete | Standard Requirement not Addressed | New York, NY USA | Unfunded | 2025-02-10 | Address the requirement: Asset Life Cycle Management |  | Security and compliance assessment | Ongoing | Security Operations | CIS1.1, CIS3.5
High | Mitigate | High | High | NIST CSF | 2.0 | ID.IM-01 | Continuous Improvements Evaluation: ID.IM-01: Improvements are identified from evaluations. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Continuous Improvements Evaluation |  | Security and compliance assessment | Ongoing | Security Operations | CRI.ID.IM-01.01, CRI.ID.IM-01.02, CRI.ID.IM-01.03, CRI.ID.IM-01.04, CRI.ID.IM-01.05
High | Mitigate | High | High | NIST CSF | 2.0 | ID.RA-08 | Vulnerability Disclosure Response: ID.RA-08: Processes for receiving, analyzing, and responding to vulnerability disclosures are established. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Vulnerability Disclosure Response |  | Security and compliance assessment | Ongoing | Security Operations | CIS7.2
High | Mitigate | High | High | NIST CSF | 2.0 | ID.RA-09 | Pre-acquisition Integrity Assessment: ID.RA-09: The authenticity and integrity of hardware and software are assessed prior to acquisition and use. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Pre-acquisition Integrity Assessment |  | Security and compliance assessment | Ongoing | Security Operations | CRI.EX.DD-04.01, CRI.EX.DD-04.02
High | Mitigate | High | High | NIST CSF | 2.0 | ID.RA-10 | Supplier Pre-Acquisition Assessments: ID.RA-10: Critical suppliers are assessed prior to acquisition. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Supplier Pre-Acquisition Assessments |  | Security and compliance assessment | Ongoing | Security Operations | CRI.EX.DD-03.01, CRI.EX.DD-03.02, CRI.EX.DD-03.03
High | Mitigate | High | High | NIST CSF | 2.0 | PR.AA-02 | Identity Binding to Credentials: PR.AA-02: Identities are proofed and bound to credentials based on the context of interactions. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: PR.AA-02: Identities are proofed and bound to credentials based on the context of interactions. |  | Security and compliance assessment | Ongoing | Security Operations | CRI.PR.AA-02.01
High | Mitigate | High | High | NIST CSF | 2.0 | PR.AA-04 | Identity Assertions: PR.AA-04: Identity assertions are protected, conveyed, and verified. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Identity Assertions |  | Security and compliance assessment | Ongoing | Security Operations | CRI.PR.AA-04.01
High | Mitigate | High | High | NIST CSF | 2.0 | PR.DS-11 | Data Backup: PR.DS-11: Backups of data are created, protected, maintained, and tested. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Data Backup |  | Security and compliance assessment | Ongoing | Security Operations | CIS11.2, CIS11.3, CIS11.5
High | Mitigate | High | High | NIST CSF | 2.0 | PR.IR-03 | Resilience Measures: PR.IR-03: Mechanisms are implemented to achieve resilience requirements in normal and adverse situations. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Resilience Measures |  | Security and compliance assessment | Ongoing | Security Operations | CRI.PR.IR-03.01
High | Mitigate | High | High | NIST CSF | 2.0 | PR.PS-06 | Secure Systems Development Practices: PR.PS-06: Secure software development practices are integrated, and their performance is monitored throughout the software development life cycle. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: PR.PS-06: Secure software development practices are integrated, and their performance is monitored throughout the software development life cycle. |  | Security and compliance assessment | Ongoing | Security Operations | CIS16.1
High | Mitigate | High | High | NIST CSF | 2.0 | RC.RP-05 | Asset Integrity Restoration: RC.RP-05: The integrity of restored assets is verified, systems and services are restored, and normal operating status is confirmed. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: RC.RP-05: The integrity of restored assets is verified, systems and services are restored, and normal operating status is confirmed. |  | Security and compliance assessment | Ongoing | Security Operations | CRI.RC.RP-05.01, CRI.RC.RP-05.02
High | Mitigate | High | High | NIST CSF | 2.0 | RC.RP-06 | End-of-Incident Determination: RC.RP-06: The end of incident recovery is declared based on criteria, and incident-related documentation is completed. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: RC.RP-06: The end of incident recovery is declared based on criteria, and incident-related documentation is completed. |  | Security and compliance assessment | Ongoing | Security Operations | CRI.RC.RP-06.01
High | Mitigate | High | High | NIST CSF | 2.0 | RS.AN-07 | Incident Data Collection & Preservation: RS.AN-07: Incident data and metadata are collected, and their integrity and provenance are preserved. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: RS.AN-07: Incident data and metadata are collected, and their integrity and provenance are preserved. |  | Security and compliance assessment | Ongoing | Security Operations | CRI.RS.AN-07.01
High | Mitigate | High | High | NIST CSF | 2.0 | RS.MA-05 | Recovery Initiation: RS.MA-05: The criteria for initiating incident recovery are applied. | Not Implemented | Standard Requirement not Addressed | New York, NY USA | Funded | 2025-03-12 | Address the requirement: Recovery Initiation |  | Security and compliance assessment | Ongoing | Security Operations | CIS17.9

## Data Security Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
Data Security Issues
The table below lists the issues discovered during the Technical Review's User Access Review, the Sensitive Data Assessment, and automated scans. The summary below ranks individual issues based upon their potential risk to the network while providing guidance on which issues to address by priority. To mitigate global risk and improve the health of the network, address issues with higher risk values first.
Risk Priority | Risk Response | Impact | Likelihood | Implementation Status | Weaknesses | Affects | Responsible Office/Organization | Resource Estimates (Funded/Unfunded/Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility
High | Mitigate | High | High | Not Implemented | Active login by Former User and Former Third Parties: Terminated users and third parties should have their accounts disabled to prevent potential unauthorized access to Personal Data. | rsadmin : R Smith mpadmin : M Plattenberg |  | Unfunded | 27-Mar-2025 | Investigate the attempted and successful logins by users marked as former users or third parties. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | Unauthorized user: As part of reviewing the user access, some users were identified as unauthorized. | The number of items detected as being associated with this Data Security Issue is more than 100 items. Generate the Reports for this assessment and review the details associated with this Technical Issue in the Risk Treatment Plan Details.xlsx report. Administrator : Administrator ahulida : A Hulida ajadmin : A Jones amcgraw@myco.com : Aaron McGraw AmericasFinestCity@myco.com : AmericasFinestCity arogers : Aaron Rogers asadmin : A Sushkov asayers@myco.com : Allen Sayers awright@myco.com : Alfred Wright az_alerts@myco.com : AZ_Alerts azure_budget@myco.com : NDS_Azure_Budget backslash : back slash bbrown@myco.com : Barry Brown Beantown@myco.com : Beantown billing@myco.com : billing BillingOps@myco.com : BillingOps BISInternal@myco.com : BISInternal BISNotifications@myco.com : BISNotifications bissdfcadmins@myco.com : BIS SDFC Admins bwillis@myco.com : Barry Willis CallExpertsGroup@myco.com : CallExpertsGroup casecreation@myco.com : casecreation CatalystProjectTeam@myco.com : CatalystProjectTeam CBTTeam@myco.com : CBTTeam CCYleads@myco.com : CCYleads CDW@myco.com : CDW cellis@myco.com : Cyndi Ellis cirt@myco.com : cirt cloudengineering@myco.com : Cloud Engineering CloudOPS@myco.com : CloudOPS CloudOps_Status_Dashboard@myco.com : CloudOps_Status_Dashboard cloudseedshipments@myco.com : Cloud Seed Shipments cloudteam@myco.com : Cloud Team contentops@myco.com : Content Ops Contractors@myco.com : Contractors contracts-agreements@myco.com : Contracts & Agreements conversionratequestions@myco.com : Conversion Rate Questions coo-dr@myco.com : COO Direct Reports CustomerChampions@myco.com : CustomerChampions Customer-Compliance@myco.com : Customer-Compliance CustomerOrganization@myco.com : CustomerOrganization CustomerServices@myco.com : CustomerServices CustomerServiceSales@myco.com : CustomerServiceSales CustomerServiceTeam@myco.com : CustomerServiceTeam dadmin : D Brown dattovsiris : Datto VSiris dbtest@myco.com : db test DC@myco.com : DC DeploymentRequest@myco.com : DeploymentRequest Design@myco.com : Design DesignReview@myco.com : DesignReview DjemaaelFna@myco.com : DjemaaelFna dkqauser@myco.com : dkqauser dolemite : Dolemite D-Town@myco.com : D-Town dweedon@myco.com : Derek Weedon dzianis.buhayenka : Dzianis Buhayenka ebland : Eric Bland ecadmin : Evgeny C esermon@myco.com : Evan Sermon esummers@myco.com : Ernie Summers exchangetest : Exchange Test. exchangetest1 : ExchangeTest1 exchnagetest2 : ExchnageTest2 fowardslash : fowared slash fsmith@myco.com : Faith Smith ftravieso@myco.com : ftravieso admin GrandPlace@myco.com : GrandPlace GulfofMexico@myco.com : GulfofMexico henry.homiller : Henry Homiller ipcadmin@myco.com : Istvan Papp-Chang isadmin : Ina Schmidt itcintegrationupdates@myco.com : ITC integration Updates jashter : Jacob Ashter jcamps : John Camps jcole : Jerry Coleman jdejesus : Jone DeJesus jgross : Janet Gross jiraadmin : Jira Admin jknight : Janet Knight jkristian : Jabez Kristian jmonae@myco.com : Janelle Monae jryan@myco.com : Jack Ryan jsadmin : J Stark jserna@myco.com : Jose Serna jsqauser@myco.com : jsqauser jtaylor@myco.com : Jessica Taylor Justice@myco.com : Justice jwadmin : J Weakland jweakland@myco.com : Joe Weakland jwhite@myco.com : Jake White jwqauser@myco.com : jwqauser LakeHula@myco.com : LakeHula La-LaLand@myco.com : La-LaLand legal@myco.com : Legal lkebede@myco.com : Lennie Kebede lsackett@myco.com : Larry Sackett lwqauser@myco.com : lwqauser MainMarketSquare@myco.com : MainMarketSquare mdavies@myco.com : Mylie Davies | New York, NY USA | Unfunded | 27-Mar-2025 | Investigate and remove all users that are not authorized as indicated in the Risk Treatment Plan and the User Access Review worksheet. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | Unauthorized asset: As part of reviewing the asset inventory, some assets were identified as unauthorized. | 176.16.1.1 176.16.1.100 176.16.1.3 176.16.1.72 176.16.1.75 176.16.1.90 176.16.1.91 176.16.1.93 176.16.1.94 176.16.1.95 176.16.1.96 176.16.1.97 176.16.1.98 176.16.1.99 CMMC-3 / 176.16.1.68 Mac mini / 10.0.0.4 OPSTR-299-EX2016 / 176.16.1.50 VIRTUAL-TEST.LOCAL / 176.16.1.57 WS-ECHEK- / 192.168.1.145 | New York, NY USA | Unfunded | 27-Mar-2025 | Investigate and remove all assets that are not authorized. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | PII in Datto Workplace Project Folder not authorized to store data: PII data has been detected as stored in a Datto Workplace Project Folder not authorized to store PII. | /Top-Level Project/ /Top-Level Project/Sub-Level Folder/ | New York, NY USA | Reallocation | 27-Mar-2025 | Investigate the unauthorized Datto Workplace Project storing PII. PII should be stored in Datto Workplace Project Folders in accordance with organization policy. |  | Datto Workplace security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | Access to a network share authorized to store Sensitive Data is unrestricted: Network shares authorized to store Sensitive Data were found as completely unrestricted (granting access to 'Everyone'). | \\DCTRLR01\NETLOGON : C:\Windows\SYSVOL\sysvol\myco.com\SCRIPTS \\DC01\SYSVOL : C:\Windows\SYSVOL\sysvol \\FILESVR01\Accounting : D:\Shares\Accounting \\FILESVR01\Human Resources : D:\Shares\Human Resources \\FILEVR01\Operations : D:\Shares\Operations \\HVSVR01\qavers : h:\qavers | New York, NY USA | Funded | 27-Mar-2025 | Investigate the network shares authorized to store Sensitive Data with unrestricted access. Limit access to the minimum necessary. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | PII on computer not authorized to store data: PII data has been detected as stored on a computer not authorized to store PII. | APPSVR01 / fe80::4183:7729:9818:eb0f%6,176.16.1.14 / Windows Server 2019 Standard DESKPC-35EGQCC / fe80::a03d:7987:35a4:7be%3,176.16.1.179 / Windows 10 Enterprise Version 2004 | New York, NY USA | Funded | 27-Mar-2025 | Investigate the unauthorized computers storing PII. PII should be stored on computers in accordance with organization policy. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | GDPR Personal Data on computer not authorized to store data: GDPR Personal Data has been detected as stored on a computer not authorized to store Personal Data. | WRKSTN10-4 / 176.16.1.133 | New York, NY USA | Unfunded | 27-Mar-2025 | Investigate the unauthorized computers storing GDPR Personal Data. Personal Data should be stored on computers in accordance with organization policy. |  | Security and compliance assessment | Complete
High | Mitigate | High | High | Not Implemented | ePHI on computer not authorized to store data: ePHI data has been detected as stored on a computer not authorized to store ePHI. | DESKPC-35EGQCC / 176.16.1.79 DESKPC-BDJFFLG / 176.16.1.63 DESKPC-F6CKERQ / 176.16.1.59 | New York, NY USA | Unfunded | 27-Mar-2025 | Investigate the unauthorized computers storing ePHI. ePHI should be stored on computers in accordance with organization policy. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | Computer with GDPR Personal Data not backed up: Computers identified as having GDPR Personal Data are documented as not having a backup agent installed. | WRKSTN10-4 / 176.16.1.133 | New York, NY USA | Unfunded | 27-Mar-2025 | Ensure that data is properly backed up on computers with GDPR Personal Data. See the Asset Inventory Worksheet for a list of computers that are documented as not having a backup agent installed. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Not Implemented | Computer with PII not backed up: Computers identified as having PII are documented as not having a backup agent installed. | WRKSTN10-1 / 176.16.1.138 WRKSTN10-4 / 176.16.1.133 WS-ECHEK- / 192.168.1.145 | New York, NY USA | Unfunded | 27-Mar-2025 | Ensure that data is properly backed up on computers with PII. See the Asset Inventory Worksheet for a list of computers that are documented as not having a backup agent installed. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Complete | Computer storing PII does not use disk encryption: Theft is the most common form of data breach. Unencrypted computer drives storing PII may allow data loss through theft. | DESKPC-35EGQCC / 176.16.1.79 DESKPC-BDJFFLG / 176.16.1.63 DESKPC-F6CKERQ / 176.16.1.59 FS01 / 176.16.1.161 WRKSTN10-1 / 176.16.1.138 WRKSTN10-4 / 176.16.1.133 WS-ECHEKHOLSKY- / 192.168.1.145 | New York, NY USA | Unfunded | 27-Mar-2025 | Implement disk encryption on computers storing PII. |  | Security and compliance assessment | Complete
High | Mitigate | High | High | Not Implemented | Computer storing GDPR Personal Data does not use disk encryption: Theft is the most common form of data breach. Unencrypted computer drives storing GDPR Personal Data may allow data loss through theft. | WRKSTN10-4 / 176.16.1.133 | New York, NY USA | Unfunded | 27-Mar-2025 | Implement disk encryption on computers storing GDPR Personal Data. |  | Security and compliance assessment | Ongoing
High | Mitigate | High | High | Complete | Computer storing ePHI does not use disk encryption: Theft is the most common form of data breach. Unencrypted computer drives storing ePHI may allow data loss through theft. | DESKPC-35EGQCC / 176.16.1.79 DESKPC-BDJFFLG / 176.16.1.63 DESKPC-F6CKERQ / 176.16.1.59 FS01 / 176.16.1.161 | New York, NY USA | Unfunded | 27-Mar-2025 | Implement disk encryption on computers storing ePHI. |  | Security and compliance assessment | Complete
High | Mitigate | Moderate | Moderate | Complete | Former User with enabled accounts: Terminated users should have their accounts disabled to prevent potential unauthorized access to Personal Data. The following active accounts designated as former users were identified. These accounts should be disabled or removed. | The number of items detected as being associated with this Data Security Issue is more than 100 items. Generate the Reports for this assessment and review the details associated with this Technical Issue in the Risk Treatment Plan Details.xlsx report. Administrator : Administrator ahilot : A Hilot ajadmin : A Jones ajones@myco.com : A Jones amcgraw@myco.com : Aaron McGraw AmericasFinestCity@myco.com : AmericasFinestCity arogers : Aaron Rogers asadmin : A Sushkov asayers@myco.com : Allen Sayers awright@myco.com : Alfred Wright az_alerts@myco.com : AZ_Alerts azure_budget@myco.com : NDS_Azure_Budget backslash : back slash bbrown@myco.com : Barry Brown Beantown@myco.com : Beantown billing@myco.com : billing BillingOps@myco.com : BillingOps BISInternal@myco.com : BISInternal BISNotifications@myco.com : BISNotifications bissdfcadmins@myco.com : BIS SDFC Admins bwillis@myco.com : Barry Willis CallExpertsGroup@myco.com : CallExpertsGroup casecreation@myco.com : casecreation CatalystProjectTeam@myco.com : CatalystProjectTeam CBTTeam@myco.com : CBTTeam CCYleads@myco.com : CCYleads CDW@myco.com : CDW cellis@myco.com : Cyndi Ellis cirt@myco.com : cirt cloudengineering@myco.com : Cloud Engineering CloudOPS@myco.com : CloudOPS CloudOps_Status_Dashboard@myco.com : CloudOps_Status_Dashboard cloudseedshipments@myco.com : Cloud Seed Shipments cloudteam@myco.com : Cloud Team contentops@myco.com : Content Ops Contractors@myco.com : Contractors contracts-agreements@myco.com : Contracts & Agreements conversionratequestions@myco.com : Conversion Rate Questions coo-dr@myco.com : COO Direct Reports CustomerChampions@myco.com : CustomerChampions Customer-Compliance@myco.com : Customer-Compliance CustomerOrganization@myco.com : CustomerOrganization CustomerServices@myco.com : CustomerServices CustomerServiceSales@myco.com : CustomerServiceSales CustomerServiceTeam@myco.com : CustomerServiceTeam dadmin : D Brown dattovsiris : Datto VSiris dbtest@myco.com : db test DC@myco.com : DC DeploymentRequest@myco.com : DeploymentRequest Design@myco.com : Design DesignReview@myco.com : DesignReview DjemaaelFna@myco.com : DjemaaelFna dkqauser@myco.com : dkqauser dolemite : Dolemite D-Town@myco.com : D-Town dweedon@myco.com : Derek Weedon dzianis.buhayenka : Dzianis Buhayenka ebland : Eric Bland ecadmin : Evgeny C esermon@myco.com : Evan Sermon esummers@myco.com : Ernie Summers exchangetest : Exchange Test. exchangetest1 : ExchangeTest1 exchnagetest2 : ExchnageTest2 fowardslash : fowared slash fsmith@myco.com : Faith Smith ftravieso@myco.com : ftravieso admin GrandPlace@myco.com : GrandPlace GulfofMexico@myco.com : GulfofMexico henry.homes : Henry Homes ipadmin@myco.com : Istvan Prant isadmin : Isa Schmidt itcintegrationupdates@myco.com : ITC integration Updates jashter : Jacob Ashter jcamps : John Camps jcole : Jerry Coleman jdejesus : Jone DeJesus jgross : Janet Gross jiraadmin : Jira Admin jknight : Janet Knight jkristian : Jabez Kristian jryan@myco.com : Jack Ryan jstradmin : J Strong jserna@myco.com : Jose Serna jsqauser@myco.com : jsqauser jtaylor@myco.com : Jessica Taylor Justice@myco.com : Justice jwadmin : J Weakston jweakston@myco.com : Joe Weakston jwhite@myco.com : Jake White jwqauser@myco.com : jwqauser LakeHula@myco.com : LakeHula La-LaLand@myco.com : La-LaLand legal@myco.com : Legal lkebede@myco.com : Lennie Kebede lsackett@myco.com : Larry Sackett lwqauser@myco.com : lwqauser MainMarketSquare@myco.com : MainMarketSquare mdavies@myco.com : Mylie Davies | New York, NY USA | Unfunded | 27-Mar-2025 | Disable or remove accounts for former users. |  | Security and compliance assessment | Ongoing

## Azure AD Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
Azure AD Issues
The table below lists the issues discovered during the Microsoft Cloud scanning of an Azure Tenant that has been assessed during the Technical Review. The summary below ranks individual issues based upon their potential risk to the information system while providing guidance on which issues to address by priority. To mitigate global risk and improve the health of the assessed environment, address issues with higher risk values first.
Risk Priority | Risk Response | Impact | Likelihood | Implementation Status | Weaknesses | Responsible Office/Organization | Resource Estimates (Funded/Unfunded/Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility
High | Mitigate | High | High | Not Implemented | Admin Multi-factor Authentication Not Registered: A misalignment between Microsoft best practices based on Microsoft Secure Score was detected related to Admin Multi-factor Authentication. The control may not be implemented or partially implemented. See Risk Report or Management Plan for recommendations. You have 4 users with administrative roles that are not registered and protected with MFA. See Users section in Azure AD assessment to view admins and MFA enablement status. For MFA to be registered, MFA must be enabled and the user must sign in and complete the multi-factor authentication registration process. | New York, NY USA | Funded | 2025-03-31 | Requiring multifactor authentication (MFA) for administrative roles makes it harder for attackers to access accounts. Administrative roles have higher permissions than typical users. If any of those accounts are compromised, your entire organization is exposed. At a minimum, protect the following roles: Global administrator, Authentication administrator, Billing administrator, Conditional Access administrator, Exchange administrator, Helpdesk administrator, Security administrator, SharePoint administrator, User administrator |  | Security and compliance assessment | Ongoing | Azure Security Operations
High | Mitigate | High | High | Not Implemented | Customer Lockbox Not Enabled: A misalignment between Microsoft best practices based on Microsoft Secure Score was detected related to Customer Lockbox Not Enabled. The control may not be implemented or partially implemented. See Risk Report or Management Plan for recommendations. | New York, NY USA | Funded | 2025-03-31 | Turning on the customer lockbox feature requires that approval is obtained for datacenter operations that grants a Microsoft employee direct access to your content. Access may be needed by Microsoft support engineers if an issue arises. There's an expiration time on the request and content access is removed after the support engineer has fixed the issue. |  | Security and compliance assessment | Ongoing | Azure Security Operations
High | Mitigate | High | High | Not Implemented | Multi-factor Authentication Not Registered: A misalignment between Microsoft best practices based on Microsoft Secure Score was detected related to Multi-factor Authentication. The control may not be implemented or partially implemented. See Risk Report or Management Plan for recommendations. You have 139 out of 148 users that are not registered and protected with MFA. See Users section in Azure AD Report for details. | New York, NY USA | Funded | 2025-03-31 | Multifactor authentication (MFA) helps protect devices and data that are accessible to these users. Adding more authentication methods, such as the Microsoft Authenticator app or a phone number, increases the level of protection if one factor is compromised. |  | Security and compliance assessment | Ongoing | Azure Security Operations
High | Mitigate | High | High | Not Implemented | Sign in Risk Policy Not Enabled: A misalignment between Microsoft best practices based on Microsoft Secure Score was detected related to Sign in Risk Policy. The control may not be implemented or partially implemented. See Risk Report or Management Plan for recommendations. You have 123 of 148 users that don't have the sign-in risk policy turned on. | New York, NY USA | Funded | 2025-03-31 | Turning on the sign-in risk policy ensures that suspicious sign-ins are challenged for multifactor authentication (MFA). |  | Security and compliance assessment | Ongoing | Azure Security Operations
High | Mitigate | High | High | Not Implemented | User Risk Policy Not Enabled: A misalignment between Microsoft best practices based on Microsoft Secure Score was detected related to User Risk Policy. The control may not be implemented or partially implemented. See Risk Report or Management Plan for recommendations. You have 123 users out of 148 that do not have user risk policy enabled. | New York, NY USA | Funded | 2025-03-31 | With the user risk policy turned on, Microsoft Entra ID detects the probability that a user account has been compromised. As an administrator, you can configure a user risk Conditional Access policy to automatically respond to a specific user risk level. For example, you can block access to your resources or require a password change to get a user account back into a clean state. |  | Security and compliance assessment | Ongoing | Azure Security Operations

## VulScan Issues
System Name |  | InfoSystem-20230112 |  | Date of Last Update |  | 2025-02-12
Company/Business Entity Name |  | Client Company |  | Date of Original POA&M |  | 2025-02-03
VulScan Issues
The table below lists the issues discovered by the vulnerability scans performed by VulScan during the Technical Review. The summary below ranks individual issues based upon their potential risk to the network while providing guidance on which issues to address by priority. To mitigate global risk and improve the health of the network, address issues with higher risk values first.
Risk Priority | Risk Response | Impact | Likelihood | Severity/CVSS | Issue | IP Address | Hostname | MAC Address | Last Detected | Implementation Status | Responsible Office/Organization | Resource Estimates (Funded/Unfunded/Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete) | Responsibility
Moderate | Mitigate | High | High | 5.3 | OpenSSH Information Disclosure Vulnerability (CVE-2016-20012) | 172.31.56.13 |  | 0E:72:29:DE:48:3F | 2025-02-21 | Not Implemented | New York, NY USA | Funded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
Moderate | Mitigate | High | High | 5 | OpenBSD OpenSSH < 9.3 Unspecified Vulnerability | 172.31.56.13 |  | 0E:72:29:DE:48:3F | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
Moderate | Mitigate | High | High | 5 | OpenBSD OpenSSH < 9.3p2 RCE Vulnerability | 172.31.56.13 |  | 0E:72:29:DE:48:3F | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
Moderate | Mitigate | High | High | 5 | OpenBSD OpenSSH 8.9 - 9.2 Unspecified Vulnerability | 172.31.56.13 |  | 0E:72:29:DE:48:3F | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
High | Mitigate | High | High | 7.5 | SSL/TLS: Report Vulnerable Cipher Suites for HTTPS | 172.31.56.11 | AC2ANBZ-ANUOAC9 | 0E:98:8F:0B:DE:99 | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
High | Mitigate | High | High | 7.5 | Diffie-Hellman Ephemeral Key Exchange DoS Vulnerability (SSL/TLS, D(HE)ater) | 172.31.56.11 | AC2ANBZ-ANUOAC9 | 0E:98:8F:0B:DE:99 | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
Moderate | Mitigate | High | High | 4.3 | SSL/TLS: Deprecated TLSv1.0 and TLSv1.1 Protocol Detection | 172.31.56.11 | AC2ANBZ-ANUOAC9 | 0E:98:8F:0B:DE:99 | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
High | Mitigate | High | High | 7.5 | SSL/TLS: Report Vulnerable Cipher Suites for HTTPS | 172.31.56.7 | AC2AMBZ-F5KK0J7 | 0E:67:8A:53:83:91 | 2025-02-21 | Not Implemented | New York, NY USA | Funded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
High | Mitigate | High | High | 7.5 | Diffie-Hellman Ephemeral Key Exchange DoS Vulnerability (SSL/TLS, D(HE)ater) | 172.31.56.7 | AC2AMBZ-F5KK0J7 | 0E:67:8A:53:83:91 | 2025-02-21 | Not Implemented | New York, NY USA | Funded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations
Moderate | Mitigate | High | High | 4.3 | SSL/TLS: Deprecated TLSv1.0 and TLSv1.1 Protocol Detection | 172.31.56.7 | AC2AMBZ-F5KK0J7 | 0E:67:8A:53:83:91 | 2025-02-21 | Not Implemented | New York, NY USA | Unfunded | 2025-03-31 | Assess the risk of this vulnerability and remediate the internal vulnerabilty as prescribed. |  | VulScan Internal Vulnerability Scan | Ongoing | IT Operations